[Trust name]

Business case: robot-assisted surgery programme

1 robot, Platform B: established multi-port (purchase)

| Prepared by | [Name, role] |
| --- | --- |
| Senior responsible owner | [Name, role] |
| Clinical lead | [Name, role] |
| Finance lead | [Name, role] |
| Date | 28 October 2026 |
| Version | Draft 0.1 |
| Status | Draft: assumptions awaiting specialty review |

DRAFT. Generated by the Robotic Programme Decision Tool, engine version 0.6.1. 53 of the 55 assumptions in the register (Appendix D) are placeholders, assumptions or only partly sourced, and none has yet been reviewed by the relevant specialty. The figures must not be used for approval until that review is complete.

# Contents

[Right-click and choose Update Field to show the contents.]

# 1. Executive summary

This business case seeks approval for a robot-assisted surgery programme at [Trust name]: 1 robot (Platform B), operating 18 of 18 available sessions per fortnight across 4 list types on the two-week theatre template.

It is presented as an investment in quality, access and capacity, not as a cost-saving proposal. The case sets out first what the investment buys for patients, then what it costs per outcome, then the extra cost to the trust over five years, and the guardrails that keep spending efficient.

### What the programme delivers for patients each year (year 3, steady state)

| Patient consequence | Number per year |
| --- | --- |
| Robotic operations | 410 |
| Open operations avoided | 140 |
| Bed-days released | 306 |
| Conversions to open surgery avoided | 9.7 |
| Major complications avoided | 5.4 |
| Returns to theatre avoided | 1.3 |
| Readmissions avoided | 0.9 |
| Extra elective operations the released beds could support | 76 |

### Cost per outcome (five years)

| Measure | Extra cost to the trust |
| --- | --- |
| Per robotic operation | £2,643 |
| Per open operation avoided | £7,767 |
| Per bed-day released | £3,759 |
| Per serious event avoided (complication, return to theatre or readmission) | £151,583 |

Each ratio divides the whole five-year extra cost by one consequence, so they must not be added. Neither 30-day cost avoided nor tariff income is deducted, so the ratios measure NHS resources used.

### Five-year cost to the trust

| £ (thousands) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Extra cost to the trust (revenue) | 960 | 963 | 1,025 | 1,020 | 1,016 | 4,984 |

Tariff: the income line counts only the difference over what the trust would earn for the same patients without the robot, entered per procedure, and assumes those patients would otherwise be treated at this trust. It appears in the trust's cash case only. It is a transfer within the NHS, so it is excluded from the economic view (net present cost) and from the cost per outcome. No extra tariff income has been entered for this case.

Capital: £1,920,000 in total, of which £920,000 is funded by the trust and £1,000,000 is assumed from central funds. Revenue cost includes depreciation and public dividend capital on the trust-funded capital, so capital and revenue must not be added.

Over five years the programme would also avoid about £709,358 of 30-day costs, mostly bed-days (1,326). These are not deducted: they release capacity, not cash, unless beds or staff are removed or reused. They are shown in the economic case.

Break-even: none. At this case mix each extra case adds more cost than it avoids at 30 days, so higher volume lowers the cost per case but never reaches break-even.

For comparison, a well-functioning benchmark programme (about 550 cases per robot a year, typical case mix, mid-level costs) would cost about £2,318 per robotic operation and £2,141 per bed-day released, against £2,643 and £3,759 here (section 3.4).

### Spending guardrails

| Check | Result | Status |
| --- | --- | --- |
| Robotic cases per robot per year | 410 | Green |
| Robot utilisation (booked sessions) | 100% | Green |
| Share of robotic cases displacing open surgery (advisory) | 34% | Amber |
| Lists less than 75% full | 3 | Amber |
| Instrument price basis | Standard discount, 15% off list | Amber |
| Platform price | Published anchor | Green |
| Platform evidence base | Established | Green |
| Benefit assumptions changed from defaults | 0 | Green |

### Recommendation

[Board recommendation to be completed by the senior responsible owner.] The board is asked to approve the preferred option subject to completion of the specialty review of assumptions, a formal price quote, an instrument price no higher than £1,275 per case, and a benefits realisation review at 12 months.

# 2. Strategic case

## 2.1 Case for change

[Describe [Trust name]'s current position: surgical waiting lists, current minimal access rates by specialty, workforce and training needs, and any existing robotic provision.]

Robot-assisted surgery is expanding across the NHS. NICE's early value assessment of robot-assisted surgery for soft tissue procedures (HTE21, April 2025) allows these systems to be used while further evidence is generated, and asks centres to collect data on costs, activity, conversion to open surgery, rates of minimal access surgery and outcomes. Robotic prostatectomy was outside its scope because it is established NHS practice. This programme commits to that data collection through its 12-month review.

National implementation guidance from NHS England and GIRFT (July 2025) asks that robotic programmes be high volume and fully used on all working days, approved through a full business case with regional stakeholders, overseen by a steering committee, and planned with capital replacement in mind. It also says that provision for recruiting and training surgical first assistants or surgical care practitioners should be built into the business case. This case is structured to follow that guidance.

## 2.2 Specialties and priorities

The programme includes specialties that NHS England has signalled as priorities for robotic access: Hysterectomy (benign and malignant), Myomectomy, Endometriosis excision, Adnexal surgery, Abdominal wall reconstruction. Other procedures scheduled are Colorectal major resection (colon and rectum), Nephrectomy and partial nephrectomy.

## 2.3 Objectives

Deliver about 410 robotic operations a year by year 3.

Avoid about 140 open operations a year in patients who would otherwise have had open surgery.

Release about 306 bed-days a year.

Keep booked robot utilisation at or above 85% (currently planned at 100%).

Report outcomes at 12 months against this case and to the NICE evidence generation plan.

# 3. Economic case

## 3.1 Method

The appraisal is a 30-day cost-consequence analysis. Costs are set alongside patient consequences (open operations avoided, bed-days, conversions, complications, returns to theatre and readmissions) without combining them into quality-adjusted life-years. Robust one-year quality-of-life data comparing robotic, laparoscopic and open surgery are not available for most procedures, so quality-adjusted life-years would have to be assumed rather than measured. Longer-term functional, oncological and hernia outcomes are not modelled.

For each specialty, the analysis asks what would have happened to the same patients without a robot (open or laparoscopic surgery, or robotic surgery at another centre in one sensitivity scenario) and applies the 30-day differences to that mix. The headline is the extra cost to the trust with no deduction for 30-day cost avoided. The economic view (section 3.7) deducts cost avoided and uses discounted cash at the HM Treasury Green Book rate of 3.5%, with capital in year 0 and residual value credited at year 5. Activity above 700 robotic cases per robot per year is flagged as an advisory guardrail; it is not cut.

Activity comes from a two-week theatre template: each session's list type and its major, medium and minor cases are mapped to procedures (Appendix A), counted over the fortnight and extrapolated to a year. Where annual demand is entered, delivered cases are limited to demand and any shortfall is reported.

## 3.2 Options appraised

| Option | Utilisation | Cases (yr 3) | Bed-days (yr 3) | 5-year extra cost | Per bed-day released | Net present cost |
| --- | --- | --- | --- | --- | --- | --- |
| Option 0: no robot | n/a | 0 | 0 | £0 | n/a | £0 |
| Option 1: 1 robot | 100% | 410 | 306 | £4.98M | £3,759 | £4.63M |
| Option 2: 2 robots | 58% | 465 | 350 | £7.36M | £4,845 | £7.46M |

Preferred option: 1 robot. Option 0 avoids all programme costs but delivers none of the patient consequences above.

## 3.3 Platform comparison

| Platform | 5-year extra cost | Per case | Net present cost | Price basis |
| --- | --- | --- | --- | --- |
| Platform A: next-generation multi-port (purchase) | £5.48M | £2,904 | £5.08M | Published anchor |
| Platform B: established multi-port (purchase) | £4.98M | £2,643 | £4.63M | Published anchor |
| Platform C: modular (managed service) | £5.72M | £3,034 | £4.52M | Illustrative |

## 3.4 Comparison with a benchmark programme

The benchmark describes a well-functioning multi-port programme run through the same model with the same clinical assumptions and unit costs, so the differences come from volume, case mix and price. Its case mix is renormalised from the three specialties (urology, general surgery and gynaecology) that made up 90% of UK NHS robotic procedures in 2024, so other specialties are excluded. Each benchmark value is sourced; values without a published source are labelled as assumptions.

| Measure | This proposal | Benchmark | Benchmark source |
| --- | --- | --- | --- |
| Robots | 1 | 1 | Benchmark set at one robot. |
| Robotic cases per robot per year (year 3) | 410 | 550 | Assumption set by the project team. No published per-robot benchmark was found. For context, UK NHS trusts reported 36,209 robotic procedures on 212 systems in 2024 (about 171 per system). That study grouped trusts by annual volume, with 500 to 750 procedures a year as its high-volume category (Donald et al, Surg Endosc 2026). |
| Case mix: urology / general and colorectal / gynaecology / other | 12% / 40% / 48% / 0% | 48% / 33% / 19% / 0% | Donald et al, Surg Endosc 2026: urology, general surgery and gynaecology made up 90% of UK NHS robotic procedures in 2024 (43.2%, 29.6%, 16.8%); the benchmark renormalises these three to 100% and excludes other specialties. Split within specialties: assumption (no published split by procedure found). |
| Open operations avoided per robot per year | 140 | 288 | Same 30-day assumptions as the trust's case (Appendix A). |
| Bed-days released per robot per year | 306 | 632 | Same 30-day assumptions as the trust's case (Appendix A). |
| Extra cost per robot per year (year 3) | £1,024,859 | £1,216,169 | Platform B capital and maintenance, instruments at the standard discount (mid-level costs); same capital source as this proposal. |
| Extra cost per robotic case (five years) | £2,643 | £2,318 | Calculated by the tool from the rows above. |
| Extra cost per open operation avoided | £7,767 | £4,433 | Calculated by the tool. |
| Extra cost per bed-day released | £3,759 | £2,141 | Calculated by the tool. |

The benchmark volume needs about 19.2 half-day session-equivalents a fortnight at this tool's cases per list, against 18 per robot assumed here. High-volume programmes reach it with longer operating days, for example three-session days (GIRFT 2025).

## 3.5 Sensitivity analysis

Each assumption is moved on its own to a low and a high value while everything else, including the list plan, stays at the base case. Bars are ordered by how much they move the result. Ranges are placeholders for expert review. The first chart shows the five-year extra cost, which clinical assumptions barely affect; the second shows the extra cost per bed-day released, which they drive.

Figure 1. One-way sensitivity: five-year extra cost to the trust.

Figure 2. One-way sensitivity: extra cost per bed-day released.

| Assumption | Low | High | Extra cost at low | Extra cost at high |
| --- | --- | --- | --- | --- |
| Instrument price per case | 30% off list | list price | £4,559,851 | £5,408,551 |
| Capital per robot | -20% | +20% | £4,666,715 | £5,301,687 |
| Surgical first assistant per robot | 0 WTE | 2 WTE | £4,684,201 | £5,284,201 |
| Extra theatre minutes per case | -50% | +50% | £4,732,972 | £5,235,430 |
| Cost per theatre minute | £8 | £20 | £4,816,715 | £5,319,173 |
| Steady-state utilisation | 80% | 100% | £4,586,563 | £4,984,201 |
| Maintenance per robot | -20% | +20% | £4,834,201 | £5,134,201 |
| Sterile services per case | half | double | £4,913,476 | £5,125,651 |
| Share of templated cases that go ahead | 85% | 100% | £4,812,631 | £4,984,201 |
| Share open without the robot (all specialties) | half | 1.5 times | £4,960,672 | £5,003,107 |

| Assumption | Low | High | Per bed-day at low | Per bed-day at high |
| --- | --- | --- | --- | --- |
| Bed-days saved per case | half | 1.5 times | £7,518 | £2,506 |
| Share open without the robot (all specialties) | half | 1.5 times | £5,412 | £2,953 |
| Instrument price per case | 30% off list | list price | £3,439 | £4,079 |
| Learning curve (years 1 and 2) | slower (50%, 75%) | none (100%) | £4,049 | £3,543 |
| Capital per robot | -20% | +20% | £3,520 | £3,999 |
| Surgical first assistant per robot | 0 WTE | 2 WTE | £3,533 | £3,985 |
| Extra theatre minutes per case | -50% | +50% | £3,570 | £3,949 |
| Cost per theatre minute | £8 | £20 | £3,633 | £4,012 |
| Steady-state utilisation | 80% | 100% | £4,015 | £3,759 |
| Maintenance per robot | -20% | +20% | £3,646 | £3,872 |
| Sterile services per case | half | double | £3,706 | £3,866 |
| Share of templated cases that go ahead | 85% | 100% | £3,889 | £3,759 |

### Scenarios

| Scenario | 5-year extra cost | Per bed-day released | Per open operation avoided | Net present cost |
| --- | --- | --- | --- | --- |
| Base case (as configured) | £4.98M | £3,759 | £7,767 | £4.63M |
| No 30-day benefit | £4.98M | n/a | £7,767 | £5.27M |
| All benefits halved | £4.98M | £7,518 | £7,767 | £4.95M |
| All benefits 1.5 times | £4.98M | £2,506 | £7,767 | £4.31M |
| Instruments: supplier list price | £5.41M | £4,079 | £8,428 | £5.01M |
| Instruments: volume discount, 30% off list | £4.56M | £3,439 | £7,106 | £4.25M |
| No central capital (trust funds all capital) | £5.81M | £4,383 | £9,056 | £4.63M |
| Central capital £2,000,000 per robot | £4.22M | £3,186 | £6,582 | £4.63M |

## 3.6 Break-even

Break-even: none. At this case mix each extra case adds more cost than it avoids at 30 days, so higher volume lowers the cost per case but never reaches break-even. The search is limited to the volume the programme could actually deliver: every available session filled at the planned cases per session.

| Measure (steady state, per year) | Value |
| --- | --- |
| Planned robotic cases | 410 |
| Maximum deliverable cases | 410 |
| Extra cost less 30-day cost avoided at the planned volume | £861,224 |
| Extra cost less 30-day cost avoided at the maximum volume | £861,224 |
| Break-even volume | not reached |

## 3.7 Economic view (net of 30-day cost avoided)

| Measure | Value |
| --- | --- |
| Net present cost to the NHS (5 years, 3.5%) | £4.63M |
| 30-day cost avoided over five years | £709,358 |
| Net cost per robotic operation | £2,267 |
| Net cost per open operation avoided | £6,662 |
| Net cost per bed-day released | £3,224 |

The net present cost counts capital in full in year 0 whoever pays it, so it does not change with central capital. 30-day cost avoided is an economic value: it becomes cash only if beds or staff are removed or the released capacity is used for income-earning activity.

## 3.8 Benefits not valued in cash

Wider access to minimal access surgery for patients who would otherwise have open surgery.

Surgical training and recruitment and retention of surgeons and theatre teams.

Ergonomic benefit to surgeons.

Capacity released by shorter stays, available for further elective activity.

# 4. Commercial case

## 4.1 Procurement route

[State the procurement route, for example the national framework for robotic medical equipment managed by NHS Supply Chain, or a competitive tender, and the evaluation criteria.] Four payment models have been compared on identical terms: outright purchase, lease, managed service and per-procedure fee.

## 4.2 Price inputs used

| Item | Value |
| --- | --- |
| Platform | Platform B: established multi-port (purchase) |
| Procurement model | Purchase |
| Capital per robot | £1,920,000 |
| Trade-in credit | £0 |
| Central capital per robot | £1,000,000 |
| Asset life | 7 years |
| Maintenance per robot per year | £150,000 |
| Instrument price per case | £1,275 (standard discount, 15% off list) |
| Price basis | Capital from a published NHS trust business case (May 2026; reference to be re-confirmed). Of the same order as an earlier NHS full business case (about £2 million capital and £150,000 maintenance a year). Instruments: US single-centre average about $1,500 per case |

## 4.3 Negotiating targets

| Target (net of 30-day cost avoided) | Instrument price per case needed |
| --- | --- |
| Current assumption | £1,275 |
| Supplier list price | £1,500 |
| Net cost of £1,500 per bed-day released | £293 |
| Budget neutral at 30 days | not achievable |

Prices are calculated at the planned steady-state volume and count 30-day cost avoided. 'Not achievable' means the target cannot be met even at zero instrument cost.

## 4.4 Contract protections sought

Instrument price fixed or capped for the contract term.

Uptime guarantee with service credits.

Training and proctoring included for an agreed number of surgeons and theatre staff.

Upgrade, replacement and trade-in terms defined in advance.

Contract volumes stated clearly as per robot or per contract.

Data access for the 12-month review and NICE evidence generation.

# 5. Financial case

The table shows the extra income and expenditure cost to [Trust name] by year. Depreciation and public dividend capital apply to trust-funded capital only. Nothing is deducted for 30-day cost avoided, which is shown below the table for information.

| £ (thousands) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Platform | 311 | 307 | 302 | 298 | 293 | 1,511 |
| Instruments | 366 | 470 | 523 | 523 | 523 | 2,405 |
| Sterile services | 22 | 28 | 31 | 31 | 31 | 141 |
| Surgical first assistant | 60 | 60 | 60 | 60 | 60 | 300 |
| Extra theatre time | 76 | 98 | 109 | 109 | 109 | 502 |
| Implementation and training | 75 | 0 | 0 | 0 | 0 | 75 |
| Theatre works | 50 | 0 | 0 | 0 | 0 | 50 |
| Extra cost to the trust | 960 | 963 | 1,025 | 1,020 | 1,016 | 4,984 |

Tariff: the income line counts only the difference over what the trust would earn for the same patients without the robot, entered per procedure, and assumes those patients would otherwise be treated at this trust. It appears in the trust's cash case only. It is a transfer within the NHS, so it is excluded from the economic view (net present cost) and from the cost per outcome.

| For information (not cash) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 30-day cost avoided | 86 | 133 | 164 | 164 | 164 | 709 |
| Extra cost less cost avoided | 874 | 831 | 861 | 857 | 852 | 4,275 |

Figure 3. Extra cost to the trust by year, with 30-day cost avoided shown for comparison.

Capital: £1,920,000 in total, of which £1,000,000 is assumed from central funds. [Confirm the capital source, the revenue budget holder, VAT treatment and the capital replacement plan.]

# 6. Management case

## 6.1 Two-week theatre template

The template (pre-filled from demand, standard day) covers 14 days, Monday to Sunday twice, with AM, PM and evening sessions on each robot. Standard hours are weekday AM and PM, with Friday PM kept for maintenance; evening and weekend sessions count only when used. 18 of 18 available sessions per fortnight are booked (100%). The fortnight is extrapolated to 45 operating weeks a year, and 100% of templated cases are assumed to go ahead.

| Procedure | Sessions per fortnight | Cases on template (year) | Demand (year) | Cases delivered | Unmet demand |
| --- | --- | --- | --- | --- | --- |
| Colorectal major resection (colon and rectum) | 6.0 | 135 | 120 | 120 | 0 |
| Nephrectomy and partial nephrectomy | 2.0 | 68 | 50 | 50 | 0 |
| Hysterectomy (benign and malignant) | 2.7 | 108 | 100 | 100 | 0 |
| Myomectomy | 0.7 | 27 | 25 | 25 | 0 |
| Endometriosis excision | 3.4 | 135 | 40 | 40 | 0 |
| Adnexal surgery | 1.1 | 45 | 30 | 30 | 0 |
| Abdominal wall reconstruction | 2.0 | 45 | 80 | 45 | 35 |
| Upper GI (anti-reflux and hiatal hernia) | 0.0 | 0 | 20 | 0 | 20 |

Total unmet demand: 55 cases a year.

### Robot 1: two-week template

|  | AM | PM | Evening |
| --- | --- | --- | --- |
| Week 1 Mon | Urology: kidney: 2 medium | Urology: kidney: 1 medium |  |
| Week 1 Tue | Gynaecology: 2 major | Gynaecology: 1 major + 1 minor |  |
| Week 1 Wed | Gynaecology: 2 major | Gynaecology: 1 major |  |
| Week 1 Thu | Colorectal: 1 major | Colorectal: 1 major |  |
| Week 1 Fri | Abdominal wall: 1 major | Maintenance |  |
| Week 2 Mon | Gynaecology: 2 major | Gynaecology: 1 major + 1 minor |  |
| Week 2 Tue | Gynaecology: 2 major | Gynaecology: 1 major |  |
| Week 2 Wed | Colorectal: 1 major | Colorectal: 1 major |  |
| Week 2 Thu | Colorectal: 1 major | Colorectal: 1 major |  |
| Week 2 Fri | Abdominal wall: 1 major | Maintenance |  |

Saturdays and Sundays are shown only where a session is in use.

## 6.2 Governance, workforce and training

[Name the robotic steering committee, its executive chair and reporting line.] The committee approves every new indication and owns delivery of this business case (GIRFT 2025).

Each specialty names a clinical benefit owner and robotic lead, and agrees a credentialing and proctoring pathway.

A surgical first assistant or surgical care practitioner is funded at 1 whole-time equivalent per robot.

Learning curve allowed for: benefits are scaled to 75% in year 1 and 90% in year 2.

Utilisation ramps from 70% in year 1 to 90% in year 2 and 100% from year 3.

## 6.3 Benefits realisation at 12 months

| Measure | Planned (year 1) | Actual | Source |
| --- | --- | --- | --- |
| Robotic operations | 287 |  | Theatre system |
| Utilisation in year 1 | 70% |  | Theatre system |
| Open operations avoided | 98 |  | Local audit |
| Bed-days released | 161 |  | Patient administration system |
| Conversions to open surgery | Track rate |  | Operation notes |
| Returns to theatre within 30 days | Track rate |  | Local audit |
| Readmissions within 30 days | Track rate |  | Patient administration system |
| Extra cost to the trust | £960,240 |  | Finance |
| Instrument cost per case | £1,275 |  | Finance |

## 6.4 Key risks

| Risk | Mitigation |
| --- | --- |
| Robot under-used | Protected sessions in job plans; shared list for smaller specialties; quarterly utilisation review. |
| Too few trained surgeons to fill the lists | Training plan by specialty agreed before go-live; proctoring funded. |
| Instrument prices rise | Price cap in contract; review at renewal. |
| Benefits smaller than assumed | Sensitivity analysis shown; specialty review of assumptions; 12-month review against plan. |
| Laparoscopic cases moved to the robot with little benefit | Monitor the share of cases displacing open surgery. |
| Training delays | Phased start by specialty; proctoring agreed in advance. |

# Appendix A. Clinical assumptions by specialty

Reductions are robotic versus the comparator, at 30 days, per case. 'Share' is the proportion of these patients who would have had that comparator without the robot. All values are best-available estimates pending specialty review; any changes from the defaults are listed in Appendix C.

| Specialty | Without the robot | Share | Bed-days saved | Conversions avoided | Complications avoided | Returns to theatre avoided | Readmissions avoided | Extra minutes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Colorectal major resection (colon and rectum) | Open | 10% | 2 | 0.0% | 4.0% | 2.0% | 1.0% | 30 |
| Colorectal major resection (colon and rectum) | Conventional minimal access | 90% | 0.5 | 5.0% | 0.5% | 0.5% | 0.0% | 20 |
| Nephrectomy and partial nephrectomy | Open | 30% | 2 | 0.0% | 3.0% | 0.5% | 0.5% | 20 |
| Nephrectomy and partial nephrectomy | Conventional minimal access | 70% | 0.3 | 3.0% | 0.5% | 0.0% | 0.0% | 15 |
| Hysterectomy (benign and malignant) | Open | 50% | 1.5 | 0.0% | 3.0% | 0.5% | 0.5% | 20 |
| Hysterectomy (benign and malignant) | Conventional minimal access | 50% | 0.2 | 3.0% | 0.5% | 0.0% | 0.0% | 20 |
| Myomectomy | Open | 80% | 1.5 | 0.0% | 3.0% | 0.0% | 0.5% | 30 |
| Myomectomy | Conventional minimal access | 20% | 0.2 | 5.0% | 0.5% | 0.0% | 0.0% | 20 |
| Endometriosis excision | Open | 20% | 1.5 | 0.0% | 2.0% | 0.5% | 0.5% | 20 |
| Endometriosis excision | Conventional minimal access | 80% | 0.2 | 3.0% | 0.5% | 0.0% | 0.0% | 20 |
| Adnexal surgery | Open | 10% | 1 | 0.0% | 1.0% | 0.0% | 0.0% | 10 |
| Adnexal surgery | Conventional minimal access | 90% | 0 | 1.0% | 0.0% | 0.0% | 0.0% | 15 |
| Abdominal wall reconstruction | Open | 70% | 1.5 | 0.0% | 3.0% | 0.5% | 1.0% | 45 |
| Abdominal wall reconstruction | Conventional minimal access | 30% | 0.2 | 2.0% | 0.5% | 0.0% | 0.0% | 30 |
| Upper GI (anti-reflux and hiatal hernia) | Open | 5% | 2 | 0.0% | 2.0% | 0.5% | 0.0% | 30 |
| Upper GI (anti-reflux and hiatal hernia) | Conventional minimal access | 95% | 0.2 | 2.0% | 0.5% | 0.0% | 0.0% | 20 |

### Rationale and sources

| Specialty | Counterfactual rationale | Evidence |
| --- | --- | --- |
| Colorectal major resection (colon and rectum) | Most suitable cases are already laparoscopic; robot displaces some open (e.g. obese, pelvic, re-do). | Versus laparoscopy: conversion 9.8% v 4.8% in elective colectomy for cancer (US national registry, Surg Endosc 2024); length of stay mean difference -0.68 days (meta-analysis, PLoS One 2015). Open share is a placeholder: 25% of major bowel cancer resections in England and Wales were open in 2023 (NBOCA 2025), and patients chosen for the robot are a selected subgroup. Versus open: expert estimate. |
| Nephrectomy and partial nephrectomy | Partial nephrectomy is often open without a robot; radical mostly laparoscopic. | Best-available estimate pending specialty review (placeholder). |
| Hysterectomy (benign and malignant) | Complex cases offered to the robot (large uterus, obesity) are often open otherwise. | Open share placeholder. In England, about half of hysterectomies were laparoscopic by 2011-17 (Madhvani et al, cited in Clark and Saridogan 2021). Effect sizes are placeholders. |
| Myomectomy | Predominantly open without a robot. | Best-available estimate pending specialty review (placeholder). |
| Endometriosis excision | Mostly laparoscopic; deep disease with bowel involvement sometimes open. | Best-available estimate pending specialty review (placeholder). |
| Adnexal surgery | Mostly laparoscopic; low value on the robot except complex masses. | Best-available estimate pending specialty review (placeholder). |
| Abdominal wall reconstruction | Most ventral and incisional repairs are open without a robot. | Flagged for review: the 30-day assumptions were set for ventral and incisional hernia repair, not abdominal wall reconstruction. Open share placeholder; open repair remains the commonest approach to hernia repair in UK national data (World J Emerg Surg 2025). |
| Upper GI (anti-reflux and hiatal hernia) | Almost all laparoscopic without a robot. | Best-available estimate pending specialty review (placeholder). |

### How the theatre template maps to procedures

Each session on the template has a list type and a number of major, medium and minor cases. The table shows which procedure each tier counts as, and the split where a tier covers several procedures. 'Not modelled' cases are costed but carry no 30-day benefit. Changes from the defaults are listed in Appendix C.

| List type | Tier | Counts as |
| --- | --- | --- |
| Colorectal | Major | Colorectal major resection (colon and rectum) 100% |
| Upper GI | Minor | Upper GI (anti-reflux and hiatal hernia) 100% |
| Abdominal wall | Major | Abdominal wall reconstruction 100% |
| Urology: prostate | Medium | Radical prostatectomy 100% |
| Urology: kidney | Medium | Nephrectomy and partial nephrectomy 100% |
| Urology: bladder | Medium | Radical cystectomy 100% |
| Gynaecology | Major | Hysterectomy (benign and malignant) 40%, Endometriosis excision 50%, Myomectomy 10% |
| Gynaecology | Minor | Adnexal surgery 100% |
| Paediatric | Major | Paediatric (e.g. pyeloplasty, fundoplication) 100% |
| Head and neck | Major | Head and neck (transoral robotic surgery) 100% |
| Any other list type or tier |  | Not modelled |

### Tariff: extra income per robotic case (cash case only)

| Procedure | Extra income per case | Source |
| --- | --- | --- |
| Colorectal major resection (colon and rectum) | £0 | No robotic price difference identified: £0. |
| Nephrectomy and partial nephrectomy | £0 | No robotic price difference identified: £0. |
| Hysterectomy (benign and malignant) | £0 | No robotic price difference identified: £0. |
| Myomectomy | £0 | No robotic price difference identified: £0. |
| Endometriosis excision | £0 | No robotic price difference identified: £0. |
| Adnexal surgery | £0 | No robotic price difference identified: £0. |
| Abdominal wall reconstruction | £0 | No robotic price difference identified: £0. |
| Upper GI (anti-reflux and hiatal hernia) | £0 | No robotic price difference identified: £0. |

# Appendix B. Unit costs and programme settings

| Input | Value | Note |
| --- | --- | --- |
| Excess bed-day | £400 | Excess ward bed-day placeholder (single-trust FOI, 2023/24: £379 including ward costs and overheads, rounded up). The national average elective inpatient cost per bed-day was £1,198 in 2024/25, but this includes treatment costs and overstates the value of a day saved at the end of a stay. Bed-days are cost avoided, not cash released, and are not deducted from the extra cost to the trust. |
| Return to theatre (non-ward) | £6,000 | Best-available estimate pending specialty review (placeholder). |
| Major complication (non-ward) | £4,000 | Best-available estimate pending specialty review (placeholder). |
| Readmission (full spell) | £2,500 | Best-available estimate pending specialty review (placeholder). |
| Conversion to open (non-ward) | £1,000 | Best-available estimate pending specialty review (placeholder). |
| Extra theatre minute | £12 | Costed by default, which is conservative. Placeholder. |
| Sterile services per robotic case | £75 | Placeholder; replace with the local sterile services charge. |
| Surgical first assistant | 1 WTE per robot at £60,000 | National guidance says provision should be built into the business case (GIRFT 2025); cost is a placeholder. Use local pay rates. |
| Theatre works per robot (one-off) | £50,000 | Placeholder; confirm with estates. |
| Implementation, training and proctoring per robot | £75,000 | One-off, year 1. Placeholder. |
| Operating weeks per year | 45 |  |
| Sessions per robot per week | 9 | One slot kept for maintenance. |
| Cases per robot per year: advisory level | 700 | Amber guardrail above this level; activity is not cut. |
| Minimum list fill | 75% | Lists below this fill are flagged. |
| Maximum cases per session | 3 | Template entries above this are flagged. |
| Share of templated cases that go ahead | 100% | Allows for cancellations. Placeholder. |
| Discount rate | 3.5% | HM Treasury Green Book. |
| Public dividend capital | 3.5% | On average net book value. |

Length-of-stay reductions include stay caused by complications, so complication and return-to-theatre costs exclude ward days to avoid double counting.

# Appendix C. Model checks

Engine version 0.6.1. The calculation engine is covered by an automated test suite including hand-calculated cases and an independent re-calculation of all cost avoided.

No clinical assumptions or unit costs were changed from the defaults.

### Warnings raised by the tool

Nephrectomy and partial nephrectomy: the template schedules 68 cases a year but demand is 50, so its lists would be only 74% full.

Endometriosis excision: the template schedules 135 cases a year but demand is 40, so its lists would be only 30% full.

Adnexal surgery: the template schedules 45 cases a year but demand is 30, so its lists would be only 67% full.

Abdominal wall reconstruction: 35 cases a year are not scheduled (45 of 80 scheduled); the template does not schedule enough cases.

Upper GI (anti-reflux and hiatal hernia): 20 cases a year are not scheduled (none scheduled); the template has no lists for it.

Gynaecology major cases: the template split (hysterectomy 40%, endometriosis excision 50%, myomectomy 10%) differs from the demand mix (hysterectomy 61%, endometriosis excision 24%, myomectomy 15%), so meeting demand for some procedures over-schedules others. Review the split in the advanced mapping table, or the demand.

# Appendix D. Assumptions register

Every input the case depends on, with its source, evidence grade, status and the person who must sign it off. 11 assumption; 3 context only; 1 flagged for review; 3 partly sourced; 26 placeholder; 2 sourced; 9 trust input. No entry has yet been reviewed by the relevant specialty.

| Assumption | Value | Source | Status | Owner |
| --- | --- | --- | --- | --- |
| Colorectal major resection (colon and rectum): annual demand (robotic cases) | 120 | Trust activity data (preset values are placeholders) | Trust input | [Colorectal clinical benefit owner] |
| Colorectal major resection (colon and rectum): share that would be open without the robot | 10% | NBOCA State of the Nation report 2025 | Context only | [Colorectal clinical benefit owner] |
| Colorectal major resection (colon and rectum): 30-day differences (bed-days, events, theatre time) | See Appendix A | Surg Endosc 2024 (US registry, conversion 9.8% v 4.8%); Trastulli et al, PLoS One 2015 (length of stay -0.68 days v laparoscopy) | Partly sourced | [Colorectal clinical benefit owner] |
| Nephrectomy and partial nephrectomy: annual demand (robotic cases) | 50 | Trust activity data (preset values are placeholders) | Trust input | [Urology clinical benefit owner] |
| Nephrectomy and partial nephrectomy: share that would be open without the robot | 30% | None found | Placeholder | [Urology clinical benefit owner] |
| Nephrectomy and partial nephrectomy: 30-day differences (bed-days, events, theatre time) | See Appendix A | Expert estimate | Placeholder | [Urology clinical benefit owner] |
| Hysterectomy (benign and malignant): annual demand (robotic cases) | 100 | Trust activity data (preset values are placeholders); preset re-split to the gynaecology major mix in v0.6 | Trust input | [Gynaecology clinical benefit owner] |
| Hysterectomy (benign and malignant): share that would be open without the robot | 50% | Clark and Saridogan 2021, citing Madhvani et al (about half laparoscopic, 2011-17) | Context only | [Gynaecology clinical benefit owner] |
| Hysterectomy (benign and malignant): 30-day differences (bed-days, events, theatre time) | See Appendix A | Expert estimate | Placeholder | [Gynaecology clinical benefit owner] |
| Myomectomy: annual demand (robotic cases) | 25 | Trust activity data (preset values are placeholders); preset re-split to the gynaecology major mix in v0.6 | Trust input | [Gynaecology clinical benefit owner] |
| Myomectomy: share that would be open without the robot | 80% | None found | Placeholder | [Gynaecology clinical benefit owner] |
| Myomectomy: 30-day differences (bed-days, events, theatre time) | See Appendix A | Expert estimate | Placeholder | [Gynaecology clinical benefit owner] |
| Endometriosis excision: annual demand (robotic cases) | 40 | Trust activity data (preset values are placeholders); preset re-split to the gynaecology major mix in v0.6 | Trust input | [Gynaecology clinical benefit owner] |
| Endometriosis excision: share that would be open without the robot | 20% | None found | Placeholder | [Gynaecology clinical benefit owner] |
| Endometriosis excision: 30-day differences (bed-days, events, theatre time) | See Appendix A | Expert estimate | Placeholder | [Gynaecology clinical benefit owner] |
| Adnexal surgery: annual demand (robotic cases) | 30 | Trust activity data (preset values are placeholders) | Trust input | [Gynaecology clinical benefit owner] |
| Adnexal surgery: share that would be open without the robot | 10% | None found | Placeholder | [Gynaecology clinical benefit owner] |
| Adnexal surgery: 30-day differences (bed-days, events, theatre time) | See Appendix A | Expert estimate | Placeholder | [Gynaecology clinical benefit owner] |
| Abdominal wall reconstruction: annual demand (robotic cases) | 80 | Trust activity data (preset values are placeholders) | Trust input | [General surgery clinical benefit owner] |
| Abdominal wall reconstruction: share that would be open without the robot | 70% | World J Emerg Surg 2025 (open repair commonest in UK national data) | Context only | [General surgery clinical benefit owner] |
| Abdominal wall reconstruction: 30-day assumptions | See Appendix A | Set for ventral and incisional hernia repair, not reconstruction | Flagged for review | [General surgery clinical benefit owner] |
| Abdominal wall reconstruction: 30-day differences (bed-days, events, theatre time) | See Appendix A | Expert estimate | Placeholder | [General surgery clinical benefit owner] |
| Upper GI (anti-reflux and hiatal hernia): annual demand (robotic cases) | 20 | Trust activity data (preset values are placeholders) | Trust input | [Upper GI clinical benefit owner] |
| Upper GI (anti-reflux and hiatal hernia): share that would be open without the robot | 5% | None found | Placeholder | [Upper GI clinical benefit owner] |
| Upper GI (anti-reflux and hiatal hernia): 30-day differences (bed-days, events, theatre time) | See Appendix A | Expert estimate | Placeholder | [Upper GI clinical benefit owner] |
| Two-week theatre template | Standard day, pre-filled from demand | Trust theatre plan | Trust input | [Theatres lead] |
| Gynaecology major cases: split by procedure | Hysterectomy (benign and malignant) 40%, Endometriosis excision 50%, Myomectomy 10% | Clinical lead's estimate (40% hysterectomy, 50% endometriosis, 10% myomectomy), being confirmed | Assumption | [Clinical lead] |
| Major, medium and minor tiers: which procedure each counts as | See Appendix A | Clinical lead's mapping (v0.6); medium tier for prostate, kidney and bladder lists | Assumption | [Clinical lead] |
| Maximum cases per session | 3 | Clinical lead's default; adjustable | Assumption | [Clinical lead] |
| Share of templated cases that go ahead | 100% | None found (cancellations and under-runs) | Placeholder | [Theatres lead] |
| Cases that map to no modelled procedure | Costed, no 30-day benefit | Project team decision (conservative) | Assumption | [Project team] |
| Extra tariff income, all other procedures | £0 | No robotic price difference identified: £0. Not checked per HRG. | Placeholder | [Finance lead] |
| Tariff: patients would otherwise be treated at this trust | Assumed | If they would otherwise go to another provider, the trust gains the whole tariff and that provider loses it: a transfer, not a gain to the NHS | Assumption | [Finance lead] |
| Tariff: payment mechanism and market forces factor | Not modelled | Elective income may be paid under aligned payment and incentive (fixed plus variable) rather than full unit prices; the market forces factor is not applied | Placeholder | [Finance lead] |
| Excess bed-day (cost avoided, not cash) | £400 | Single-trust FOI 2023/24 (£379); national context: UK Parliament written answer UIN 100046, December 2025 (elective bed-day £1,198, 2024/25) | Placeholder | [Finance lead] |
| Return to theatre (non-ward) | £6,000 | None found | Placeholder | [Finance lead] |
| Major complication (non-ward) | £4,000 | None found | Placeholder | [Finance lead] |
| Readmission (full spell) | £2,500 | None found | Placeholder | [Finance lead] |
| Conversion to open (non-ward) | £1,000 | None found | Placeholder | [Finance lead] |
| Extra theatre minute | £12 | None found | Placeholder | [Finance lead] |
| Sterile services per robotic case | £75 | None found; sterilisation requirements are listed for consideration in system choice (GIRFT 2025) | Placeholder | [Finance lead] |
| Platform price basis | Platform B: established multi-port (purchase) | Capital from a published NHS trust business case (May 2026; reference to be re-confirmed). Of the same order as an earlier NHS full business case (about £2 million capital and £150,000 maintenance a year). Instruments: US single-centre average about $1,500 per case | Partly sourced | [Procurement lead] |
| Instrument price per case | £1,275 | US single-centre average about $1,500 per case; single-port extra $1,170 to $1,820 (AUA 2022 abstract MP32-10) | Placeholder | [Procurement lead] |
| Instrument discounts (15% standard, 30% volume) | 15% and 30% | None found | Placeholder | [Procurement lead] |
| Sessions per robot per week; operating weeks | 9; 45 | Programmes should be fully used on all working days (GIRFT 2025) | Assumption | [Senior responsible owner] |
| Utilisation ramp (years 1 to 5) | 70%, 90%, 100%, 100%, 100% | None found | Assumption | [Senior responsible owner] |
| Learning curve on benefits (years 1 to 5) | 75%, 90%, 100%, 100%, 100% | None found | Assumption | [Senior responsible owner] |
| Implementation, training and proctoring per robot | £75,000 | None found; GIRFT 2025 asks the business case to consider proctoring arrangements, including funding | Placeholder | [Senior responsible owner] |
| Theatre works per robot (one-off) | £50,000 | None found | Placeholder | [Estates lead] |
| Surgical first assistant or care practitioner | 1 WTE per robot at £60,000 | NHS England and GIRFT, Implementation of robotic-assisted surgery in England, July 2025 (provision should be built into the business case); cost is a placeholder | Partly sourced | [Theatres lead] |
| Robotic cases per robot per year: advisory level | 700 | Project team decision (amber guardrail above this level, not a cut) | Assumption | [Project team] |
| Minimum list fill before a list is created | 75% | Project team decision (matches the utilisation guardrail) | Assumption | [Project team] |
| Benchmark programme volume | 550 cases per robot per year | Assumption set by the project team. No published per-robot benchmark was found. For context, UK NHS trusts reported 36,209 robotic procedures on 212 systems in 2024 (about 171 per system). That study grouped trusts by annual volume, with 500 to 750 procedures a year as its high-volume category (Donald et al, Surg Endosc 2026). | Assumption | [Project team] |
| Discount rate (economic case) | 3.5% | HM Treasury Green Book (3.5% discount rate) | Sourced | [Finance lead] |
| Public dividend capital | 3.5% | DHSC policy rate | Sourced | [Finance lead] |

# Appendix E. References

National Institute for Health and Care Excellence. Robot-assisted surgery for soft tissue procedures: early value assessment. HealthTech guidance 742 (HTE21). London: NICE, April 2025.

NHS England, Getting It Right First Time. Implementation of robotic-assisted surgery (RAS) in England. London: NHS England, July 2025.

Donald N, Sebastian J, Preziosi G. National adoption of robotic-assisted surgery in the United Kingdom: a decade of growth, distribution and speciality trends (2014-2024). Surg Endosc 2026; 40: 4358-67.

HM Treasury. The Green Book: central government guidance on appraisal and evaluation. London: HM Treasury, 2022.

HM Treasury. Guide to developing the project business case (Five Case Model). London: HM Treasury, 2018.

Does the pre-conversion platform matter? A comparison of laparoscopic and robotic converted to open colectomies. Surg Endosc 2024. doi:10.1007/s00464-024-11079-0.

Trastulli S, Cirocchi R, Desiderio J, et al. Robotic versus laparoscopic approach in colonic resections for cancer and benign diseases: systematic review and meta-analysis. PLoS One 2015; 10: e0134062.

National Bowel Cancer Audit. State of the Nation report 2025. London: Healthcare Quality Improvement Partnership, 2025.

Clark TJ, Saridogan E. Is there still need for a further randomised controlled trial on the route of hysterectomy for benign disease? Facts Views Vis Obgyn 2021; 13: 103-05.

Robotic surgery in emergency general surgery: an overview of UK practice. World J Emerg Surg 2025. doi:10.1186/s13017-025-00658-8.

UK Parliament. Hospital beds: costs. Written question UIN 100046, answered 22 December 2025.

Kishore, Khairnar MR, Burton E, Sidana A, Saini S. Single-port vs. multi-port robotic radical prostatectomy: an umbrella review of meta-analyses. J Robot Surg 2026; 20: 821.

Wallace BK, Dishong DM, Cohen AJ. Single-port robotic prostatectomy is associated with higher same-day discharge and reduced length of stay: a NSQIP analysis. World J Urol 2026 (published online Sept 10).

Abaza R, Murphy C, Bsatee A, Brown DH Jr, Martinez O. Single-port robotic surgery allows same-day discharge in majority of cases. Urology 2021; 148: 159-65.

Single port robotic urologic surgery: fewer ports, higher costs. American Urological Association Annual Meeting 2022 (abstract MP32-10).

[Add local and national references as required.]